Global Initiative in Childhood Cancer

Working Groups

| Working group title [Primary Pillar] | Key topics (DRAFT) | Expected deliverables and Timeline (DRAFT) | People |
| --- | --- | --- | --- |
| Integrating childhood cancer into national policies [Policies] | - National cancer control planning - Cancer Control Plan development - Plan implementation, monitoring and evaluation - Integrating pediatrics and cancer into national policies | 6 national implementation case studies (across all 6 WHO regions) by May 2019 | WHO NVI TBD |
| Access to comprehensive care including medicines & technologies [Access] | - Medicines & technologies for management - Access – supply chain, pooled procurement and pre-qualification - People-centered supportive care (services for nutrition, infectious diseases, palliative care integration, survivorship) | Feasibility study / accessibility of essential medicines for children with cancer by May 2019 Delineate key diagnostic tests and technologies by Apr 2019 Define services and priorities for comprehensive care by June 2019 | WHO EMP, SDS, NVI IAEA TBD |
| Strengthening centres of excellence, networks & workforce capacity [Quality] | - Core components of centres and referral networks - Workforce needs & estimations - Infrastructure projections and need estimations - Resource appropriate guidelines - Programme strategies including early diagnosis | 6 national case studies with maps of existing centres, networks, and current workforce strategic plans by May 2019 | WHO NVI, HWF IAEA TBD |
| Information systems and costing [Quality/Policies] | - Population-based registries and linkages to hospital-based registries - Supporting registry development and implementation - Integration of data systems (including clinical) | Primer / policy brief(s) on childhood cancer needs in registration by May 2019 Definition framework for national investment cases by Apr 2019 | WHO HSF, NVI IARC IAEA TBD |
| Advocacy, community engagement, communications [Access/Policies] | - Roles of non-governmental organizations - Roles of parent groups - Psychosocial support & treatment support - Resource mobilization strategies | Messaging for childhood cancer – guide by May 2019 | WHO NVI, GCM TBD |

EMP = WHO Department of Essential Medicines and Health Products; GCM = Global Coordination Mechanism on NCDs; HSF = WHO Health Systems Financing; HWF = WHO Health Workforce; IARC = International Agency for Research on Cancer; NVI = WHO Department for Management of Noncommunicable Diseases, Disability, Violence and Injury Prevention; PAHO = Pan-American Health Organization; SDS = WHO Department of Service Delivery and Safety; TBD = To be determined

Expected deliverables relevant to all groups:

- Identify needs and gaps

- Identify existing resources and assets

- Identify additional resources and assets that are needed

- Outline strategies to secure resources and create assets to address needs and gaps